Reporting sheet for the implementation of National programme on

“Education for sustainable development”

(as of the end of 2018)

| No | Programme/project content |  |  | Execution |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | National programme on ESD Government resolution 209 of 2018 |  |  | Programme aims to disseminate education for sustainable development to public in order to engrain the trend on protecting the environment and cultural heritage, reducing the impact of climate change, adapting to climate change, reducing the disaster risk, applying environmentally friendly, resource efficient and healthy consumption pattern for all Mongolian citizens to contribute towards Mongolia’s sustainable development. |  |  |  |  |  |  |
| 2. | Funding sources |  |  | State and local budget, international loan, grant and other |  |  |  |  |  |  |
| 3. | Implementer/duration |  |  | Main implementing agencies: MET, MECSS |  |  |  |  |  |  |
|  |  |  |  | Partners: Other ministries, aimag and capital city governor’s offices, National statistical office, NCLE, ITPD |  |  |  |  |  |  |
| 4. | Programme goals |  |  | Goal 1. Integrating the aspects of environmentally friendly, resource efficient and profitable consumption pattern, healthy and safe lifestyle into the training curriculum by revising the content in pre-school, primary, secondary, vocational and university education, and strengthening the capacity of human and technical resource for education Goal 2: Introducing the principles of sustainable consumption and production to public communities, private entities and government organizations and engaging the participation of all stakeholders in order to associate them into activities Goal 3: Permanently upgrading the public education for sustainable development and providing sufficient and quality service to public by improving the access of information Goal 4: Improving the harmonization of all sectors’ policies and programmes by implementing the principles of education for sustainable development and promoting the collaboration and inter-sectorial coordination |  |  |  |  |  |  |
| 5. | Cost | Budget (total required cost) |  | 45 billion and 890 million MNT is required to implement the project. 2 billion and 615 million MNT was projected for 2018. |  |  |  |  |  |  |
|  |  | Out of which: |  | Budget (2018) |  | Performance |  |  | Percentage |  |
|  |  | ESD project /MECSS-Component 1/ /MET-Component 2/ |  | 741,000 CHF Component-1 394,000 Component-2 347,000 |  | 671,000 CHF Component -1 344,000 Component -2 327,000 |  |  | 90,6 % 87,0 % 94,2 % |  |
|  |  | Umnugobi aimag |  | 18,0 mln |  | 18,0 mln |  |  | 100 % |  |
|  |  | FWRNCC |  | 268,8 mln |  | 268,8 mln |  |  | 100 % |  |
| 6. | Programme goals: |  |  | Work performances |  |  |  |  |  |  |
|  | Within the framework of goal 1: |  |  | Component -1 /MECSS/ Research and assessment was done for core curriculum and textbooks of primary, lower and upper secondary education: - Analysis was done for core curriculum and textbooks of primary, lower and upper secondary education and evaluation is given. - Nationwide study was conducted for all core curriculums and recommendations are done. - In-service teachers, who have worked for 5, 10 years have received methodological training on implementing ESD principles - Schools are supported for implementing ESD principles in school management and evaluation. Component -2 /MET/ 37 new schools and kindergarten are enrolled in international eco-school network. Currently there are 292 / 288 school, 4 KG/ enrolled. On 7th November, “IV eco-school forum” was organized. 45 eco-schools, who are actively working to disseminate ESD was granted environmental assessment equipments worth 4 mln MNT each. 11 schools were selected and awarded with a grant of 16,500,000 each to implement small projects on ESD, SD and GD. “Green passport” campaign, which aims to bring up children eco-friendly and promote healthy lifestyle and right attitude was started from March 2018. The campaign focuses on the following 9 themes; water, waste, climate change, green environment, responsible citizenry, eco-friendly tourism, collection of waste batteries and energy. Eco club students and teachers conducted nature practice training at Ogii lake research center, Arkhangai aimag. During the campaign, 50000 students acquired green passport to get involved in sustainable development campaigns. As the end of 2018, 50,000 students and total of 90,000 teachers, students and citizens became the holder of green passport. Within the cooperation with UN GGGI, “Green economy and model” training curricula was developed in collaboration with NUM, Institute of Finance and Economy and Mongolian Life Sciences University teacher teams, handout was printed, 25 ToTs were prepared. The module has been streamlined into the training starting from academic year 2018. “Sustainable financing” training module, which will be streamlined into bachelor level study of the universities was developed. National Olympiads on biology, ecology and microbiology was organized in collaboration with the National University of Mongolia. |  |  |  |  |  |  |
|  | Within the framework of goal 2: |  |  | Component -2 /MET/ “Business green exit” training, which aims to provide assistance on implementing environmental management system was held 4 times involving over 300 participants from business entities in UB, Dornogobi and Umnugobi. “Business green exit -2018” forum was held on 16 November 2018. The 5 standards were translated from English to Mongolian and are ready to be approved by Standardization organization of Mongolia: *Darkhan-uul branch of National University of Medical Sciences was qualified for ISO 14001 standard. Stakeholder discussion on “Sustainable consumption” was organized on 24 August, with the support from EU SWITCH-Asia programme. The cooperation with the programme is planned to start from 2019 and the work plan was developed at the discussion and now waiting for financial approval. “Green technology-energy efficiency 2018” exhibition was held with the cooperation with Chamber of trade and commerce of Mongolia on 28-29 May. Over 60 organisations and 500 people participated in the exhibition. Together with UN Finance Initiative and Mongolian banking association, the Ministry implemented the project on “Mapping of sustainable financing of Mongolia”, which developed its mapping report in Nov 2018. “Sustainable financing-2018” national forum was held on 10 December on the topic of “Mapping of sustainable financing: expanding from banking sector”. With the cooperation with UN GGGI, “Green economy and model” training curricula was developed in collaboration with NUM, Institute of Finance and Economy and Mongolian Life Sciences University teacher teams, handout was printed, 25 ToTs were prepared. The module has been streamlined into the training starting from academic year 2018. “Sustainable economy” training module, which will be taught for bachelor students was developed. The Minister’s decree А/122, issued on 7th May, 2018 established a committee to award “Green certificate” and a technical committee to award “Eco label” to the citizens and business entities, who introduced eco-friendly, advanced technology into their businesses. The selection criteria for the award were developed and the stakeholders’ discussion was held. The selection methodology including recommendations and suggestions developed by the discussion was approved by the Minister’s resolution. |  |  |  |  |  |  |
|  | Within the framework of goal 3: |  |  | Component -2 /MET/ Between 2016-2017, the ESD project built capacities of journalists through series of trainings on SD and GD. The Ministry cooperated with team of national trainer journalists to publish the first edition of “Change” quarterly magazine. A training for 280 specialists and state inspectors of environmental department of 21 aimags, GASI and representatives of small miners was organized from 4-5 October. The training aimed to give knowledge and information on chemical substances that have been prohibited for mining and ways to decrease the usage. SD-GD information and data is uploaded onto http://www.nogoon.mn site, run by Datacom, available for public to use. “One root” NGO is responsible for administration of the website. |  |  |  |  |  |  |
|  | Within the framework of goal 4: |  |  | Component -2 /MET/ Development of aimag Green development policy and action plans for Orkhon, Dornogobi, Darkhan-Uul and Tuv aimags were supported by UN GGGI and ESD projects. As a result the policy documents were developed and approved by local citizens’ representative meetings. Green construction council, headed by the deputy minister of Construction and urban development, held its first meeting on 13 April and started project on development of green construction assessment system with the assistance from International finance corporation. A MoU was signed between MET, MCUD and IFC to collaborate to establish assessment system for green construction. Recommendations of MET to be synchronized with Government policy on construction and possible collaboration for developing green construction were submitted to the Ministry of construction and urban development on 19 November, 2018. |  |  |  |  |  |  |
| 7. | Conclusion |  |  | Phase 2 of the project is recommended to be implemented from 2019 for continued sustainability of results and successes achieved, and disseminate knowledge and practices gained. |  |  |  |  |  |  |
| 8. | External assessor’s evaluation for stakeholder cooperation |  |  | Collaboration of client, implementing partners, funder to be detailed here. |  |  |  |  |  |  |
| 9. | Assessment for the programme implementation (self assessment) |  | Performance | Number of goals | Goal 1 |  | Goal 2 | Goal 3 |  | Goal 4 |
|  |  |  | % | 4 | 100 % |  | 100 % | 100 % |  | 100 % |
| 10. | Final assessment for programme implementation (By cabinet secretariat) |  |  | Final assessment |  |  |  |  |  |  |
|  |  |  |  | ... % |  |  |  |  |  |  |